## Slide 1
Jan
Feb
Mar
Apr
May
Jun
3rd Read and Approval at Academic Senate
Kristy will take Annual Update Template to Eric The Coder
1/14/2019
Annual Update Due Date
3/22/2019
Training Session 12-2pm
2/6/2019
Training Session 12-2pm
2/13/2019
Launch template campus wide
36 days
To Do List:
R&R will finalize Budget Planning Timeline
Identify when template should be submitted to the Finance Office
62 days
41 days
34 days
39 days
Draft Annual Update Budget Planning Timeline
1st Read at The Council
1/18/2019
2nd Read and Approval at The Council
1/25/2019
2/4/2019
R&R The Council Finance Office (Early June)
Note: Timeline between R&R and the Council TBD by R&R and presented to IP&B